## Slide 1
Unit 4: Monitoring and Evaluation (M&E)
Multi-Sectoral Nutrition Action Planning Training Module

## Slide 2: Unit Purpose
Plan how to track progress towards the identified goal and objectives.

## Slide 3: Unit Objectives
Identify indicators for nutrition objectives, strategies, and activities.
Develop an M&E Framework and Communication Plan for monitoring nutrition interventions in the district/LLG.

## Slide 4
Developing the M&E Framework
Session 4.1

## Slide 5: Introducing M&E
M&E: Monitoring is the routine tracking of a programme's activities by measuring on a regular, ongoing basis whether planned activities are being carried out. It is used to track changes in programme performance over time. Evaluation measures the extent to which change occurs consistent with programme objectives.
M&E helps to improve performance and achieve results.
The goal of M&E is to improve current and future management of activities.
M&E establishes links between past, present, and future actions.

## Slide 6: Why Is M&E Important?
Helps us plan.
Helps us track the use of resources and effectiveness of interventions and activities.
Helps us stay on track towards meeting the goal and objectives and identify whether changes are needed.

## Slide 7: Indicator – Definition
A quantitative or qualitative variable that provides a valid and reliable basis for assessing or measuring achievement, performance, or change resulting from a strategy or activity.
Data or statistics that describe a person, place, or an event and/or the changes in it.

## Slide 8: Quantitative versus Qualitative
Quantitative: Data in numerical form that can be put into categories, ranked, or measured.
  Example: Number of health facilities built in the past 12 months.
  Methods/sources: Routine program data, closed questionnaires (yes/no), observation.
Qualitative: Descriptive information that examines beliefs, perceptions, and behaviours.
  Example: What are the causes of poor nutrition in the community?
  Methods/sources: Focus group discussions (FGDs), semi-structured interviews (SSIs), observations.
Notes: Closed questionnaires for example are those with yes/no questions

## Slide 9: Types of Indicators
Output indicator: Measures the quantity of goods and services produced and the efficiency.
  Example: Number of boreholes constructed during Q1.
  Can be used to measure progress of strategies and activities
Outcome indicator: Measures the broader results achieved through the provision of goods and services, such as a change in behaviour.
  Example: Increase in exclusive breastfeeding rates among children 0–6 months from 40% to 60% within 5 years.
  Can be used to measure objectives and goal over the long term

## Slide 10: Other Key Terms
Baseline: A measure taken before an intervention or activity has started against which progress can be measured.
Target: Also called ‘milestones’, targets tell us what we plan to achieve at specific points during projects or programmes.

## Slide 11: M&E Framework
The M&E Framework should include:
  Indicators to be used for monitoring strategies and activities and for tracking progress towards the goal and objectives.
  Data sources.
  Baseline information (if available).
  Annual and total targets.

## Slide 12: M&E Framework
Sn | Indicator | Data collection method | Frequency of collection | Department/ partner responsible for collection | Baseline | Annual Targets |  |  |  |  | Total Target
 |  |  |  |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | 
1 | % of children under 5 who had diarrhoea in the past 2 weeks | Household survey | Annually | Health | 25% | 23% | 15% | 10% | 7% | 5% | 5%
1.1 | % of households in coverage area access water from village borehole | Household survey | Annually | Water | 17% | 15% | 25% | 50% | 75% | 100% | 100%
1.1.1 | % of villages with borehole | Observation/ administrative records | Quarterly | Water | 12% | 10% | 25% | 50% | 80% | 90% | 100%

## Slide 13: Contributing to Global Targets
Remember, your MSNAP will help contribute to global targets. Uganda, as a SUN country, is assessed using a common framework. Think about how your plan contributes.
Step 1 – How multiple stakeholders from different sectors come together to address all forms of malnutrition.
Step 2 – How multiple stakeholders from different sectors change their behaviours to advocate, partner and commit towards common results.
Step 3 – How multiple stakeholders mobilize resources and align their implementation to optimize coverage and effectiveness of their actions.
Step 4 – How effective results are achieved through aligned implementation in a far greater way than what could have been achieved by each stakeholder on its own.
Step 5 – How results contribute to better nutrition status of children, adolescents, women and vulnerable groups.
Step 6 – How better nutrition will contribute to key SDGs by 2030.

## Slide 15: Sharing Results
Once you identify the information you want to collect, you also need to think about how to use it.
Stakeholders working on nutrition activities should report data to their NCC.
NCCs should report on nutrition activities both down to the LLGs and up to national level.

## Slide 16: M&E Group Work
Complete your M&E Framework.
  Identify at least one indicator for each item in your Results Framework.
  If you have time, begin working on setting targets.
  Ensure that the indicator numbering matches the numbering in the Results Framework so that the indicators can be linked to specific objectives, strategies, and activities.
Develop an M&E Communication Plan.
  Who are the main M&E data users?
  What are their data needs?
  Who collects and analyses the data?
  How will the data be communicated to stakeholders? Through what specific means?
  How will lessons learned be identified and shared?

## Slide 17: M&E Gallery Walk
Session 4.2

## Slide 18: M&E Gallery Walk
Display your flip charts on the wall.
  One team member stays with the flip chart to present and get feedback.
  Other team members visit the other displays to get ideas and give feedback.

## Slide 19: Discussion Questions
Were any of your indicators similar?
Did you see new indicators or ideas that could be added to your M&E Framework or Communication Plan?

## Slide 20: After the Sharing
Return to groups to share feedback and ideas from other teams.
Make revisions as needed.

## Slide 21: Update the MSNAP Template
Using the results of Unit 4, you can complete drafting the following section of your MSNAP:
Monitoring and Evaluation Plan